## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | USDrinkDelight:001 | Design Documentation for Backend application | Sreenad | Sriharsha | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | USDrinkDelight:002 | Test Plan | Sreenad | Sriharsha |  | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | USDrinkDelight:003 | Bootstrapping the project | Sreenad | Sriharsha | Simple | Low | RD:1 Application SetUp | RD: DrinkDesignDocument_ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | USDrinkDelight:004 | Entity Class and Table Design and Populating the data | Sreenad | Sriharsha | Complex | Low | RD2: Entity Class Design and RD3: Table Design | RD:DrinkDelightDesinDocument_ver2 | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | USDrinkDelight:005 | Displaying Distributor Details for the given DistributorId, and Stock Details for the given orderId | Sreenad | Sriharsha | Average | Low | RD 4: Displaying the Distributor and Stock Details | RD:DrinkDelightDesinDocument_ver3 | Functional |  |  |  |  | 16 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
5 | 6 | Work session | High | USDrinkDelight:006 | Update Exit,Manufacture,Expiry Date for particular OrderId | Sreenad | Sriharsha | Complex | Low | RD7: Update Date for orderId | RD: DrinkDelightDesinDocument_ver4 | Functional |  |  |  |  | 16hrs | TC_Service_02,TC_DAO_02, TC_UI_03
6 | 7
7 | 8
8 | 9
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | USDrinkDelight:007 | Design Documentation fo Angular application | Sreenad | Sriharsha | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement | Non Functional
| 17 | Standard document | High | USDrinkDelight:008 | Test Plan
16 | 18 | Standard document |  | USDrinkDelight:009 | Design a home page having standard menus
17 | 19 |  |  | USDrinkDelight:010 | Place an order
18 | 20
19 | 21
20 | 22
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USDrinkDelight:007 | 1 | Wireframes and story boarding for each task | Vijay
|  | 2 | Routing Url List | Vijay
|  | 3 | Data classes details | Murali
|  | 4 | Angular service | Sriharsha
|  | 5 | Components details | Sriharsha
|  | 6 | Detail about the security | SaiTeja
| USDrinkDelight:008 | 1 | Test Plan for Place an order
|  | 2 | Test Plan for product stock management
| USDrinkDelight:009 | 1 | Designing menu in template
|  | 2 | Adding Routing details
|  | 3 | Displaying standard info o
| USDrinkDelight:010 | 1 | Design a form that displays order ,stock details and add the distributor
|  | 2 | Component sends the details to service
|  | 3 | Angular service make the webservice call and get the Order Id ref from the backend
|  | 4 | Design a web design to display generated orderID or error response sent by the server
List User Story steps that were not completed at Sprint End
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USDrinkDelight:001 | 1 | Entity Class Design | Murali | 2020-04-15 | 4 hrs | 2 hrs | Completed | 3
|  | 2 | Table Design | Murali | 2020-04-15 | 2 hrs | 2 hrs | Completed | 2
|  | 3 | Application Architecture | Vijay | 2020-04-15 | 1 hrs | 0.5 hrs | Completed | 1
|  | 4 | Use case diagram | SaiTeja | 2020-04-15 | 2 hrs
|  | 5 | Sequence Diagram | Sriharsha | 2020-04-15 | 4 hrs
|  | 6 | Each use case detail description | SaiTeja | 2020-04-15 | 4 hrs
|  | 7 | Activity Diagram | Vijay | 2020-04-15 | 1 hrs
|  | 8 | Class Diagram | Sriharsha | 2020-04-15 | 2 hrs
|  | 9 | Webservice URL Details | Vijay | 2020-04-15 | 2 hrs
2 | USDrinkDelight:002 | 1 | Test plan for dao,
|  | 2 | Test plan for service
|  | 3 | Test plan for webservice methods
3 | USDrinkDelight:003 | 1 | Creating a Spring boot starter project | Sriharsha | 2020-04-17 | 2 hrs | 0.5 hrs |  | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Sriharsha | 2020-04-17 | 1 hrs | 0,5 hrs |  | 0,5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Sriharsha | 2020-04-17 | 1 hrs | 0,5 hrs |  | 0,5 hrs
4 | USDrinkDelight:004 | 1 | Entity Class Design | Murali
|  | 2 | Check tables are poulated in DB | SaiTeja
|  | 3 | Populate the Data | Vijay
5 | USDrinkDelight:005 | 1 | Write a JPQL query to retrieve the Distributor details for the given DistributorId, src and destination in DAO layer
|  | 2 | service method invoke the Dao and get the list. If distributor is empty throw DistributorException "No Distributor Found"
|  | 3 | REstController method get the details such as name,address,phone,url path and send to service
6 | USDrinkDelight:006 | 1 | Write the JPQL query to get the stock details by orderID in DAO
|  | 2 | Write the JPQL query to update exitDate by order ID in DAO
|  | 3 | Write a JPQL query to update manufacturing date ,expiry date and quality check by order ID in DAO
|  | 4 | Service checks the order Id and validate date
|  | 5 | If date is valid
|  | 6 | update the Dates and bind to particular order id and send to DAO
|  | 7 | RestController method get the details such as stock details and send to service method and returns success message
7 | USDrinkDelight:007 | 1 | Create a method to get the order details by orderId in DAO
|  | 2 | DAO gets the order details of that partitular OrderId
|  | 3 | Service method invokes the DAO and get the order details
|  | 4 | RestController get the details of that particular orderId. If that id is not present it throws an "OrderIdNotFoundException"
8 | USDrinkDelight:008 | 1 | Create a method to update the DeliveryStatus by orderId in DAO
|  | 3 | Status will be updated and bind to the particular orderId in the DAO
|  | 4 | Service method invokes the DAO and gets the successfully updated message and send to the RestControllerLayer
|  | 5 | RestController return that message. If id is not found it throws an "OrderIdNotFoundException"
9 | USDrinkDelight:009 | 1 | Write a JPQL Query to display the list of order and get details of the particular distributor Id
|  | 2 | DAO gets the list of order with paticular distributorId and send back to ServiceLayer
|  | 3 | Service method invokes the DAO and get the list of Orders with Paticular distributorId and send back to RestControllerLayer.
|  | 4 | RestController will get the details of orders if distributorId is present in distributorTable else it throws exception "DistributorId not Found"
10 | USDrinkDelight:010 | 1 | Write a JPQL Query to display the list of order and get details of the particular distributor Id and Delivery Status.
|  | 2 | DAO gets the list of order with paticular distributorId and DeliveryStatus send back to ServiceLayer
|  | 3 | Service method invokes the DAO and get the list of Orders with Paticular distributorId and deliveryStatus send back to RestControllerLayer.
|  | 4 | RestController will get the details of orders if distributorId and DeliveryStatus is present in distributorTable else it throws exception "DistributorId with deliverystatus not Found"
11 | USDrinkDelight:011 | 1 | Write the JPQL query to display the list of products are available in the spec and get the GetProductDetails in DAO Layer
|  | 2 | DAO gets the list of products and send back to Service Layer
|  | 3 | Service method invokes the DAO Layer and get the productList send back to RestController
|  | 4 | RestController get the list of the productDetails from the URL path and send it to the service component
12 | USDrinkDelight:012 | 1 | Write the JPQL query to post the placeAnOrder in DAO Layer
|  | 2 | Write the persist Method to place the order DAO Layer and send back to Service Layer
|  | 3 | Service method invokes the DAO Layer and post the PlaceAnOrder and send back to RestController
|  | 4 | RestController Post the PlaceAnOrder from the URL path and send it to the Service Component
13 | USDrinkDelight:013 | 1 | Write the JPQL query to delete the order details by orderId in DAO Layer
|  | 2 | Write the remove Method to delete the order by orderId in DAO Layer
|  | 3 | DAO checks weather the orderId is present or not and send back to Service Layer
|  | 4 | Service Method invokes the DAO Layer and get the orderId and send back to RestController
|  | 5 | RestController delete the order by the orderId from the URL Path if orderId is Found else if OrderId is notFound then it throws an ProductOrderException
List User Story steps that were not completed at Sprint End
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.